## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2231-swen-261-04-sam-and-friends
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page.
Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page.
Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute.
Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description.
Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket.
As a Developer I want to create a funding basket so that helpers can add needs from the cupboard to the funding basket. | Given the funding is created when adding a need to my funding basket then I expect to see the need appear in the funding basket.
As a helper, I want to add needs to my funding basket so that I can help the organization. | Given a list of needs, when I select a need, then I expect to be able to add it to my funding basket.
As a Developer, I want to add the ability to create helper accounts to my so that they can fund the organization’s needs. | Given I type in a username other than admin when I log in then I expect to be brought to the helper page.
Given a list of needs, when I select a need, then I expect to be able to add it to my funding basket.
As a helper, I want to fund a need so that the need can be finished. | Given a need exists when I fund a need then I expect to see the funds I added go towards the need.
As a user I want to be able to log in and out so that I can view my funding basket. | Given I am not logged in when I launch the website then I expect to be able to log in as a helper or u-fund manager.
As a Developer I want to unit tests so that I can ensure the functionality of my code. | Given methods are already made when run my unit tests then I expect to see that all the unit tests pass.
As a Developer, I want to create more unit tests so that I can ensure that my methods work. | Given I have methods in a class when I write unit tests for them then I expect to see the tests pass and an overall coverage above 90% .
As a Ufund Manager, I want to upload files so that to the helpers can see where their money is going. | Given a file I want to upload when I upload the file then I expect to see the contents of the file displayed on the screen.
As a helper, I want to fund a need so that the need can be finished. | Given a need exists when it is being funded then I expect to see a progress bar that reflects how much the need has been funded
As a U-fund Manager, I want to show that a need has been accomplished so helpers can see that the need is finished. | Given a need has been fully funded when move it to a finished needs list then I expect to see the need displayed with other finished needs.
As a U-fund Manager, I want to edit the text on the about page so that helpers can see updated information about the company. | Given I am on the about page when I update the text then I expect to see the updated text on the about page.
As a Developer, I want to create more unit tests so that I can ensure that my methods work. | Given I have methods in a class when I write unit tests for them then I expect to see the tests pass and an overall coverage above 90% .
As a U-fund Manager, I want a need to be removed from the cupboard once it is funded so helpers can see that the need is finished. | Given a need exists when its quantity reaches 0 then I expect to see the need removed form the cupboard and JSON file.
As a Developer I want to update the design documentation so that our design process is easy to see. | Given the old design doc when I open the design doc file then I expect to see the updated design doc
As a developer, I want to improve the look of the website so that helpers like the way it looks. | Given a page exists when I navigate to the page then I expect to see the page with updated CSS that is cohesive with the rest of the pages.